## Instructions
INLC Strategic Plan - SharePoint Import Template
PURPOSE:
This workbook contains your complete 2030 Strategic Plan structured for import into SharePoint.
Each tab represents a SharePoint list with matching column names.
TABS:
• Objectives: 3 main strategic objectives
• Strategies: 19 strategies linked to objectives
• Tactics: Specific action items linked to strategies (28 samples included)
• KPIs: Key Performance Indicators linked to tactics (17 samples included)
HOW TO USE:
1. REVIEW & EDIT: Review each tab and fill in missing information (Owner names, dates, etc.)
2. ADD MORE TACTICS: The Tactics tab has 28 sample tactics. Add all remaining tactics from your plan.
3. PARENT IDs: Notice the 'ParentObjectiveID', 'ParentStrategyID' columns - these create relationships:
- Strategies link to Objectives via ParentObjectiveID (e.g., STR-001 → OBJ-001)
- Tactics link to Strategies via ParentStrategyID (e.g., TAC-001 → STR-001)
- KPIs link to Tactics via ParentTacticID (e.g., KPI-001 → TAC-001)
IMPORTING TO SHAREPOINT:
1. Create your SharePoint lists first (follow Claude's step-by-step guide)
2. Copy data from each Excel tab
3. Paste into corresponding SharePoint list using 'Edit in grid view'
4. Import in order: Objectives → Strategies → Tactics → KPIs (parent must exist before child)
IMPORTANT NOTES:
• Column names match SharePoint exactly (e.g., 'LeadDepartment' not 'Lead Department')
• IDs use format: OBJ-001, STR-001, TAC-001, KPI-001
• Dates should be MM/DD/YYYY format
• Status values must match SharePoint choices exactly
• Owner column will use person picker in SharePoint - leave names blank or use email format
NEXT STEPS:
1. Complete filling in this workbook with all your tactical details
2. Follow Claude's SharePoint setup guide to create your lists
3. Import this data into your SharePoint lists
4. Set up Power Automate flows for automation
5. Build PowerBI dashboard for visualization
Questions? Refer back to the comprehensive SharePoint implementation guide Claude provided.

## Objectives
ObjectiveID | Title | Description | LeadDepartment | Owner | StartDate | TargetDate | Status | Priority
OBJ-001 | Develop and execute a robust portfolio of well-resourced conservation projects to achieve key milestones towards our 2030 goal | Focus on protecting 15,000 acres through priority area projects in WA and ID. Maintain full project pipeline striving to move at least 50 projects through Evaluation and Development by 2030. | Conservation |  | 01/01/2025 | 12/31/2030 | In Progress | High
OBJ-002 | Build a broader community of conservation allies and champions by (re)connecting people to the land and expanding partnerships, education, and engagement opportunities | Expand community engagement through Glen Tana, develop Idaho presence, build tribal partnerships, launch Future Leaders program, and hire Engagement Director. | Engagement |  | 01/01/2025 | 12/31/2030 | In Progress | High
OBJ-003 | Diversify and grow the human and financial resources of our organization to achieve long term conservation impact | Create multi-year staff and board recruitment plans, implement facilities and technology improvements, expand member and corporate partner recruitment, develop donor stewardship portfolios, and build resilient funding model. | Executive |  | 01/01/2025 | 12/31/2030 | In Progress | High

## Strategies
StrategyID | ParentObjectiveID | Title | Description | LeadDepartment | Owner | StartDate | TargetDate | Status | Priority
STR-001 | OBJ-001 | Define INLC's service area and complete 50+ priority area projects | Implement Priority Area plan, conduct annual outreach with 50 landowners and 20 conservation professionals, define service area with partner land trusts, develop stable of inactive projects ready for funding. | Conservation |  | 01/01/2025 | 12/31/2030 | In Progress | High
STR-002 | OBJ-001 | Define Community Conservation objectives and criteria | Define Community Conservation Project criteria including willing landowners, feasibility, project duration. Develop project selection and evaluation tool. Clarify policy for Conservation Opportunity and Special Projects fund. | Conservation |  | 01/01/2025 | 09/30/2025 | In Progress | High
STR-003 | OBJ-001 | Implement strategic process for agency relationship building | Track and maintain relationships with regional elected officials. Plan for and launch Advocacy Committee to secure conservation funding and planning support. | Conservation |  | 01/01/2025 | 12/31/2027 | In Progress | Medium
STR-004 | OBJ-001 | Develop Conservation Buyers cohort and mini-campaign strategy | Plan and launch Conservation Buyers cohort cultivation strategy. Plan for ongoing project-specific mini-campaigns to fund completion of specific projects. | Philanthropy |  | 01/01/2025 | 12/31/2027 | Not Started | Medium
STR-005 | OBJ-001 | Host landowner gathering and expand landowner engagement | Host inaugural landowner gathering to share resources and build community. Build processes for evaluating and funding restoration projects. | Stewardship |  | 01/01/2025 | 12/31/2027 | Not Started | Medium
STR-006 | OBJ-002 | Launch and expand Leveraging Glen Tana community engagement strategy | Phase 1: House demolition and site prep. Expand community engagement programming. Plan for Phase 2 site build-out and capital campaign. | Engagement |  | 01/01/2025 | 12/31/2029 | In Progress | High
STR-007 | OBJ-002 | Expand Idaho engagement and donor development | Fill project pipeline with compelling ID projects. Plan and implement ID community engagement activities. Develop 1 new high-visibility Community Conservation site in ID. | Conservation |  | 01/01/2025 | 12/31/2028 | In Progress | High
STR-008 | OBJ-002 | Build intentional relationships with regional Tribes | Plan for intentional relationship building with regional Tribes. Partner in hosting regional Tribal/Land Trust gathering. Create plan for inviting tribal representation into INLC board leadership. | Executive |  | 01/01/2025 | 12/31/2028 | In Progress | High
STR-009 | OBJ-002 | Launch Future Leaders internship program | Plan Future Leaders internship program structure and budget to develop next generation of conservation leaders. Launch program in 2026. | Engagement |  | 01/01/2025 | 12/31/2027 | Not Started | Medium
STR-010 | OBJ-002 | Hire Engagement Director and expand engagement programming | Budget and plan for Engagement Director position. Hire director and expand programming, branding, marketing. Launch expanded marketing/branding campaign. | Engagement |  | 01/01/2025 | 12/31/2027 | Not Started | High
STR-011 | OBJ-002 | Expand volunteer stewardship program | Continue existing volunteer engagement. Seek corporate partners to fund expanded volunteer stewardship program on conserved lands. Launch expanded program with Engagement Director. | Stewardship |  | 01/01/2025 | 12/31/2028 | In Progress | Medium
STR-012 | OBJ-002 | Occupy office space/facilities by 2027 | Assess current and future facilities needs via staff survey. Develop criteria for desired facilities. Create and implement timeline and funding plan for new/improved office spaces. | Operations |  | 01/01/2025 | 12/31/2027 | In Progress | High
STR-013 | OBJ-002 | Conduct org-wide tech systems audit and develop multi-year plan by 2026 | Conduct systems audit by end of 2025 prioritizing cyber security. Hire managed IT consultant. Develop 5-year plan for hardware/software acquisition, maintenance, and replacement. | Operations |  | 01/01/2025 | 12/31/2026 | In Progress | High
STR-014 | OBJ-003 | Create multi-year staff and board recruitment and development plans | Create and implement staff and board recruitment plans. Intentionally seek diverse backgrounds for open positions. Launch recruitment and development plans in 2026. | Executive |  | 01/01/2025 | 12/31/2027 | Not Started | High
STR-015 | OBJ-003 | Use strategic plan to evaluate organizational effectiveness | Implement strategic plan to evaluate, redirect, celebrate staff and board effectiveness. Learn from and update plan/metrics to maintain momentum and relevance. | Executive |  | 01/01/2025 | 12/31/2030 | In Progress | High
STR-016 | OBJ-003 | Sustain and expand member and corporate partner recruitment | Sustain existing member and corporate partner recruitment. Plan and budget for elevated programs. Implement expanded recruitment plans starting 2027. | Development |  | 01/01/2025 | 12/31/2029 | In Progress | High
STR-017 | OBJ-003 | Implement and expand donor stewardship portfolios | Implement expanded staff donor stewardship portfolios. Plan and implement board donor stewardship portfolios. Evaluate and adapt continuously. | Philanthropy |  | 01/01/2025 | 12/31/2029 | In Progress | High
STR-018 | OBJ-003 | Develop culture of philanthropy through training | Plan ongoing fundraising trainings and philanthropy team-building for staff and board. Implement training plan. Plan and implement Philanthropy Team recruitment. | Philanthropy |  | 01/01/2025 | 12/31/2028 | Not Started | Medium
STR-019 | OBJ-003 | Research and implement resilient funding model | Research funding models of similar-sized nonprofits. Plan for resilient, balanced revenue mix. Implement funding diversification plan. | Development |  | 01/01/2025 | 12/31/2028 | Not Started | High

## Tactics
TacticID | ParentStrategyID | Title | Description | Owner | DueDate | Status | PercentComplete | Priority | Phase
TAC-001 | STR-001 | Resource delegation for Priority Area plan implementation | Determine goals for outreach and projects within each priority area. Delegate staff hours. Develop and maintain 10 projects per conserve staff member. |  |  | In Progress | 40 | High | Ongoing
TAC-002 | STR-001 | Complete annual outreach with landowners and professionals | Conduct outreach with 50 landowners and 20 conservation professionals throughout INLC service area. Document conservation barriers. |  | 12/31/2025 | In Progress | 30 | High | 2025
TAC-003 | STR-001 | Define INLC service area with partner land trusts | Work with Palouse Land Trust to delineate work areas in Shoshone County. Continue communication with Kaniksu Land Trust for Bonner County. |  | 06/30/2025 | In Progress | 50 | High | 2025
TAC-004 | STR-001 | Develop stable of inactive projects ready for funding | Build pipeline of projects that are fully prepared but awaiting funding sources. |  |  | Not Started | 0 | Medium | Ongoing
TAC-005 | STR-002 | Define a Community Conservation Project | Define criteria: What is a willing landowner? How does feasibility affect selection? How long should a project take? Bring proposal through LPC. |  | 09/30/2025 | In Progress | 60 | High | 2025
TAC-006 | STR-002 | Develop project selection and evaluation tool | Create evaluation tool for assessing Community Conservation Projects. |  | 09/30/2025 | In Progress | 50 | High | 2025
TAC-007 | STR-002 | Clarify policy for Conservation Opportunity and Special Projects fund | Conserve team makes proposals for policy changes. Reviewed by directors, approved by board. |  | 12/31/2025 | Not Started | 0 | Medium | 2025
TAC-008 | STR-012 | Assess current and future facilities needs - survey staff | Survey staff for what they want to see. Develop criteria for desired future facilities including office space, education space, plant nursery, or other spaces. |  | 06/30/2026 | Not Started | 0 | High | 2026
TAC-009 | STR-012 | Create and implement timeline and funding plan for new office space | Create and implement timeline and funding plan for acquiring new office space(s) or improving existing spaces. |  | 12/31/2027 | Not Started | 0 | High | 2027
TAC-010 | STR-013 | Conduct systems audit by end of 2025 | Conduct org-wide tech systems audit. Develop implementation plan and budget that prioritizes cyber security. |  | 12/31/2025 | In Progress | 40 | High | 2025
TAC-011 | STR-013 | Hire consultant for full-service managed IT | Hire consultant to provide full-service managed IT. Designate in-office tech contact to work with consultant. REACH OUT TO OTHER NONPROFITS about what they're doing. |  | 03/31/2026 | Not Started | 0 | High | 2026
TAC-012 | STR-013 | Develop 5-year plan for hardware and software | With assistance from consultant, develop plan and budget for acquiring, maintaining, and/or replacing hardware and software for next 5 years. |  | 06/30/2026 | Not Started | 0 | High | 2026
TAC-013 | STR-006 | Launch Phase 1 of Leveraging Glen Tana: House demolition and site prep | Complete house demolition and prepare site for community engagement activities. |  | 12/31/2025 | In Progress | 30 | High | 2025
TAC-014 | STR-006 | Continue and expand community engagement programming at Glen Tana | Develop and implement community engagement programming offerings at Glen Tana site. |  |  | Not Started | 0 | Medium | 2026-2027
TAC-015 | STR-006 | Develop plans for Phase 2: Site build-out | Create comprehensive plans for Glen Tana Phase 2 facility build-out. |  | 12/31/2027 | Not Started | 0 | Medium | 2027
TAC-016 | STR-007 | Fill project pipeline with compelling ID projects | Continue filling pipeline with compelling Idaho projects that will inspire more ID support. |  |  | In Progress | 30 | High | Ongoing
TAC-017 | STR-007 | Plan for ID community engagement activities | Plan and implement ID community engagement activities. Use ID projects to recruit, retain, develop ID donors. |  | 12/31/2026 | Not Started | 0 | High | 2026
TAC-018 | STR-007 | Develop 1 new high-visibility Community Conservation site in ID | Identify, develop, and launch one high-visibility Idaho community conservation site. |  | 12/31/2027 | Not Started | 0 | High | 2027
TAC-019 | STR-008 | Plan for intentional Tribal relationship building | Plan for intentional relationship building with regional Tribes. Continue nurturing existing relationships. |  | 12/31/2025 | In Progress | 30 | High | 2025
TAC-020 | STR-008 | Partner in hosting regional Tribal/Land Trust gathering | Partner with Tribes to host regional Tribal/Land Trust gathering. |  | 12/31/2026 | Not Started | 0 | High | 2026
TAC-021 | STR-008 | Create plan for inviting Tribal representation into board | Create plan for inviting tribal representation into INLC board leadership positions or advisory capacity. |  | 12/31/2026 | Not Started | 0 | High | 2026
TAC-022 | STR-010 | Budget and plan for Engagement Director position | Develop job description, budget, and hiring plan for Engagement Director and program. |  | 06/30/2026 | Not Started | 0 | High | 2026
TAC-023 | STR-010 | Hire Engagement Director | Execute recruitment process and hire Engagement Director. |  | 12/31/2026 | Not Started | 0 | High | 2026
TAC-024 | STR-010 | Plan and launch expanded marketing/branding campaign | Develop and implement expanded marketing and branding campaign to increase visibility and membership. |  |  | Not Started | 0 | Medium | 2026-2027
TAC-025 | STR-014 | Create multi-year staff recruitment and development plan | Develop comprehensive multi-year plan for staff recruitment and professional development. |  | 12/31/2025 | Not Started | 0 | High | 2025
TAC-026 | STR-014 | Create multi-year board recruitment and development plan |  | 12/31/2025 | Not Started | 0 | High | 2025
TAC-027 | STR-014 | Launch staff and board recruitment and development plans | Begin implementation of recruitment and development strategies for both staff and board. |  |  | Not Started | 0 | High | 2026
TAC-028 | STR-014 | Intentionally seek diverse applicants for open positions | Actively recruit applicants of diverse backgrounds and experience for all open staff positions. |  |  | In Progress | 40 | High | Ongoing

## KPIs
KPI_ID | Title | ParentTacticID | ParentTacticID: TacticID | Objective | Lead_Department | Scenario | Description | Metric_Type | Target_Value | Current_Value | Unit | Frequency | Last_Updated | Data_Source
KPI-001 | Acres conserved (annual) | TAC-001 |  | OBJ-001 | Conservation | Base | Annual acres permanently conserved toward 15k goal by 2030 | Acres | 3000 | 0 | acres | Annual | 2025-10-17 |  | GIS tracking system
KPI-002 | # of priority conservation projects completed or in pipeline | TAC-001 |  | OBJ-001 | Conservation | Base | Cumulative count of priority projects toward 50+ by 2030 | Count | 50 | 12 | projects | Quarterly | 2025-10-17 |  | Project scheduler
KPI-003 | # of landowners and professionals engaged | TAC-002 |  | OBJ-001 | Conservation | Base | Landowners and advisors engaged through outreach events and site visits | Count | 70 | 15 | contacts | Annual | 2025-10-17 |  | CRM system
KPI-004 | % of conservation easements monitored | TAC-001 |  | OBJ-001 | Stewardship | Base | Annual monitoring of all conservation easements to ensure 100% compliance | Percentage | 100 | 85 | % | Annual | 2025-10-17 |  | Stewardship database
KPI-005 | # of restoration projects funded/underway | TAC-001 |  | OBJ-001 | Stewardship | Base | Number of funded habitat restoration projects on conserved lands | Count | 10 | 3 | projects | Annual | 2025-10-17 |  | Stewardship reports
KPI-006 | Landowner stewardship gatherings hosted | TAC-001 |  | OBJ-001 | Stewardship | Base | Annual gatherings to engage and support conservation landowners | Count | 2 | 1 | events | Annual | 2025-10-17 |  | Event calendar
KPI-007 | Volunteer & community participants engaged | TAC-014 |  | OBJ-002 | Engagement | Base | Annual count of volunteers, students, and community participants engaged | Count | 500 | 250 | people | Annual | 2025-10-17 |  | Volunteer database
KPI-008 | Volunteer stewardship events hosted | TAC-014 |  | OBJ-002 | Engagement | Base | Number of volunteer events or workshops hosted per year | Count | 20 | 8 | events | Annual | 2025-10-17 |  | Event tracking
KPI-009 | New community conservation site in Idaho | TAC-018 |  | OBJ-002 | Conservation | Base | Establishment of a high-visibility Idaho site for community conservation | Yes/No | 1 | 0 | site | One-time | 2025-10-17 |  | Project records
KPI-010 | Tribal partnership engagement events | TAC-020 |  | OBJ-002 | Executive | Base | Annual or biannual gatherings with Tribal partners to support shared conservation goals | Count | 1 | 0 | events | Annual | 2025-10-17 |  | Partnership calendar
KPI-011 | Tribal representation in governance | TAC-021 |  | OBJ-002 | Board | Base | Inclusion of Tribal members in board/advisory roles | Yes/No | 1 | 0 | members | One-time | 2025-10-17 |  | Board records
KPI-012 | Future Conservation Leaders internships | TAC-022 |  | OBJ-002 | Engagement | Base | Internship program for underrepresented groups in conservation | Count | 5 | 0 | interns | Annual | 2025-10-17 |  | HR records
KPI-013 | Total active members/donors | TAC-025 |  | OBJ-003 | Development | Base | Annual number of individual donors contributing to INLC | Count | 1500 | 1200 | donors | Annual | 2025-10-17 |  | CRM/donation tracking
KPI-014 | Major donors engaged | TAC-025 |  | OBJ-003 | Development | Base | Number of major donor prospects actively cultivated | Count | 50 | 35 | donors | Quarterly | 2025-10-17 |  | Major gifts pipeline
KPI-015 | Private philanthropy % of revenue | TAC-025 |  | OBJ-003 | Development | Base | Proportion of annual revenue from private donations, grants, and bequests | Percentage | 60 | 55 | % | Annual | 2025-10-17 |  | Financial reports
KPI-016 | Annual operating revenue | TAC-025 |  | OBJ-003 | Finance | Base | Total annual revenue supporting operations and growth | Currency | 3000000 | 2500000 | $ | Annual | 2025-10-17 |  | Financial statements
KPI-017 | Office/facilities expansion | TAC-009 |  | OBJ-003 | Operations | Base | Secure and occupy expanded office facilities by 2027 | Yes/No | 1 | 0 | completion | One-time | 2025-10-17 |  | Facilities plan