## OBJECTIVE 2
INLAND NORTHWEST LAND CONSERVANCY (INLC) |  | Color Codes:
2030 Plan Implementation |  | Red: Start now
Green: Start later
VISION: People across our region collaborating together to conserve the natural lands, waters, and open spaces that sustain and enrich life, fostering nature's resilience for generations to come |  | Yellow: Start is conditional on something else
MISSION: Protect and care for the lands and waters essential to life and the well-being of communities in the Inland Northwest.
2030 GOAL: Accelerate the permanent protection of 15K acres of priority lands, habitats, and open spaces in the region.
OBJECTIVES | STRATEGIES | TACTICS/PLANS | METRICS | TEAM LEADS | TEAM SUPPORT | ANTICIPATED CAPACITY AND BUDGET IMPLICATIONS |  |  | SEQUENCE AND SCHEDULE OF WORK | [21 empty] | KEY DATES
[9 empty] | FY25 | [11 empty] | FY26 |  |  |  | FY27 |  | FY28 |  | FY29
[6 empty] | 2025 | 2026 |  | Jan | Feb | Mar | April | May | June | July | Aug | Sept | Oct | Nov | Dec | Q1 | Q2 | Q3 | Q4 | Q1/Q2 | Q3/Q4 | Q1/Q2 | Q3/Q4 | Q1/Q2 | Q3/Q4
1. Develop and execute a robust portfolio of well-resourced conservation projects to achieve key milestones toward our 2030 goal. | Strategy #1: Define INLC’s service area and complete Evaluation and Development of 50+ priority area projects in WA and ID by 2030. | TACTIC 1 - Resource delegation for implementation of the Priority Area plan. Determine goals for outreach and projects with in each Priority area (updated annual work plans.) Delegate staff hours needed to complete annual goals. | Outreach onDevelop and maintain 10 projects per conserve staff member in the development folder. | Mike |  |  |  | Currently staffed up. | ONGOING
|  | TACTIC 1A: Public Communication of this plan |  | Carol |  | 2500 |  | Staff time Graphics and Printing Costs
|  | TACTIC 2 - Complete annual outreach with 50 landowners and 20 conservation professionals throughout the INLC service area. Document conservation barriers that prevent successful permanent land protection. |  | Conserve Team |  |  |  | Currently staffed up.
|  | TACTIC 3: To define INLC's service area, work with Palouse Land Trust to delineate our work areas in Shoshone County. Continue to communicate with Kaniksu Land Trust when projects are located in Bonner County. Work in partnership when it benefits the project. | INLC's Serv ice Area Defined Each staff stewards a list of XX conservation professional and land managers. | Mike |  |  |  | Currently staffed up.
|  | Tactic 4: Develop a "stable" of inactive projects that are ready to go and waiting on funding. |  | Todd |  |  |  | Currently staffed up.
|  |  |  | Mike |  |  |  | Currently staffed up.
| Strategy #2: Define "Community Conservation" objectives and criteria by Q3 2025 to ensure intentionality, rigor, and structure to land protection projects that serve Objective #2. | Tactic 1 - Define a Community Conservation Project. What is a willing landowner? How does feasibility effect selection? How long should a project take? Bring proposal. Go through LPC. Engage members of community--what level? PLEASE KEEP IN MIND THAT COMMUNITY CONSERVATION PROJECT SELECTION WILL REMAIN A BIT MORE SUBJECTIVE. LET'S NOT TRY TO CREATE A COMPLETELY OBJECTIVE TOOL FOR IDENTIFYING AND SELECTING | Outreach through the RCO Cons Planning process. Engaging community leaders. Working with nonprofits. Tribal input. | Todd | Mike |  |  | Currently staffed up.
|  | Tactic 2 - Develop project selection and evaluation tool for Community Conservation Projects. | Outcome will be a evaluation tool that we fill out when evaluating a Community Conservation Project | Todd | Mike |  |  | Currently staffed up.
|  | Tactic 3 - Clarify policy and uses for the Conservation Opportunity and Special Projects fund. | Conserve team make proposals for changes to policy. Reveiwed by directors. Approved by board. | Conserve Team | Dave |  |  | Currently staffed up. | [6 empty] | Dave Out | Dave Out | Dave Out
| Strategy #3: Deepen collaboration with organizational and agency partners and funders to maximize success in our priority areas and with "community conservation" projects. | Tactic 1: Expand conservation partnerships with organizations that support land protection. Explore more funding through State and Federal sources. | Identify funding gaps for all projects. Funding sources: RCO, RCPP, ALE, Forest Legacy, Restoration Partnership. | Mike |  |  |  |  | ONGOING
|  | Tactic 2: Leverage partnerships with higher capacity conservation organizations to get projects done. | Fill project funding gaps with private funding sources. | Mike | Dave | [9 empty] | Dave Out | Dave Out | Dave Out
|  | Tactic 3: Remain nimble, adaptive, and resilient WRT shifting conservation funding landscape |  | All | [10 empty] | Dave Out | Dave Out | Dave Out
|  | Tactic 4: Anticipate and lean into complex funding strategies | Develop a plan for micro-campaigns for funding. Expand a list of conservation buyer by 3X. Link federal/state funding with private org funding. | Mike | All
| Strategy #4: Enhance and restore the conservation values of our properties by maintaining strong landowner relationships, monitoring and ensuring 100% easement compliance, and securing $XK for this work by 2030. | TACTIC 1: Develop or implement more robust monitoring tools including remote programs, aerial monitoring options like LightHawk, and fine-tune Landscape to capture a more thorough annual report for protected properties. | All properties monitored annually using 33% less staff time and resources. | Rose | _ |  |  | Identify costs in 2025, and incorporate hire of additional CE steward before 2030. |  |  | RESEARCH |  | USE AND MAINTAIN REMOTE MONITORING SYSTEMS AS NEEDED TO MEET 33% STAFF TIME REDUCTION
|  | TACTIC 2: Develop and implement a model that would identify high priority conserved properties for restoration including factors like partner service area or interest, wetland or stream data, wildlife data, adjacency, etc. | Create a set of at least 10 priority restoration properties, and conduct outreach by 2030. | Rose | Mike (?) |  |  | GIS, stewardship staff time. | [6 empty] | R&D OF MODEL |  | USE MODEL
|  | TACTIC 3: Seek out restoration partners, corporate partners, or funding sources that could implement INLC-facilitated restoration projects on private lands or preserve properties identified in the new model. | All "active" restoration projects are supported by conservation partner expertise and fully funded by grants or corporate partners | Rose | Carol or Maria(for corp. partner support) |  |  | Project dependent - determine costs as we go, and plan to get them fully funded by grants or other funders. | [6 empty] | INTERVIEW PARTNERS |  | USE MODEL, RECRUIT SUPPORT/FUNDING
|  | TACTIC 4: Host regular (annual or bi-annual) landowner gatherings and communications to build community, enhance trust with the organization, and to introduce landowners to resources that may help them improve habitat value or land use practices on their easement properties. | ___% conversion to members/donors, reduction in potential violations and active communication, more landowner-led habitat enhancement projects conducted. | Rose | Maria (communication tools) |  |  | Identify costs in 2025 | PLANNING |  |  | IMPLEMENTATION AND MAINTENANCE | [8 empty] | PLAN | IMPLEMENT |  |  | PLAN | IMP. | PLAN | IMP. | PLAN | IMP.
|  | TACTIC 5: Build capacity to carry out stewardship projects by training a portion of the "future leaders" in field study, monitoring, and best practices to expand the impact of the stewardship team on protected lands, including partner project lands and privately held conservation easement properties. | Supports tactic #1, all properties monitored annually using 33% less paid staff time and resources. | Rose | _ |  |  | Identify costs in 2025 | PETE RESEARCHING | [11 empty] | TRAIN INTERNS PER TEAM PLAN
| Strategy #5: Catalyze conservation support and outcomes by informing Spokane and Kootenai County land use decisions and county/state funding, and supporting the advocacy platforms of the Idaho Coalition of Land Trusts (ICOLT) and Washington Association of Land Trusts (WALT). | Tactic 1: Recruit an Advocacy Committee chair | Committee chair picked and committee formed | Board Chair
|  | Tactic 1A: Recruit committee members. Adopt Committee Charter. Define staff liaison roles, responsibilities and capacity |  | Advocacy Chair
|  | Tactic 2: Become more closely informed of and engaged in WALT, LTA, and ICOLT advocacy positions and process, transferring knowledge back to INLC Advocacy Committee |  | Advocacy Committee | Advocacy Committee Staff Liaison
|  | Tactic 3: Create an Advocacy Committee work plan that adequately scans the landscape and anticipates land use planning issues/opportunities, conservation funding issues/opportunities in order to respond and engage in a timely, proactive manner |  | Advocacy Chair | Advocacy Committee
|  | TACTIC 3A: Engage the public/our supporters in our advocacy "asks" |  | Maria
|  | Tactic 4: Create a tracking and reporting mechanism for documenting successes and setbacks in order to evaluate whether the effort is resulting in more land conserved |  | Advocacy Chair
| (Pending merger with DHC) Strategy: Create, integrate, and advance a new Dishman Hills Priority Area and conservation plan. | Begin outreach for adjacent landowners and DHC prioirty properties. |  | Mike | DHC Committee |  |  | YES
2. Build a broader community of conservation allies and champions by (re)connecting people to the land and expanding partnerships, education, and engagement opportunities. | Strategy #1: Formulate a clear vision and implementation plan by QX of X year for retaining, investing in, and fully leveraging part of the Glen Tana parcel as a large-scale, inclusive, and publicly accessible engagement platform for conservation. | TACTIC 1: Develop and present a short-term ownership vision, budget, and funding plan to the board that addresses the liability of the house while leaning in to the opportunities of the nursery, preserve management, and community engagement (possibly with some "temporary" program improvements like a shelter) | Plan created, presented, adopted? | Dave | Rose and Steven |  |  | Time: Steven, Rose, and Dave | [6 empty] | Dave Out | Dave Out | Dave Out
|  | TACTIC 1A: Implement short-term plan | Plan implemented? | Rose | Steven | TBD - From Rose and Steven |  | Cost: Demolition and site prep costs (perhaps donated?) |  |  | Fundraise/Friendraise
|  | TACTIC 1B: Plan and implement community engagement programming at GT using the "temporary" site improvements | People engaged Program funding secured | Maria | Steven |  |  | Time: Steven, Engagement staff Costs: Program costs
|  | TACTIC 2: Develop and present a long-term ownership vision, budget, and funding plan to the board that fully leverages the property as a large-scale, inclusive, and publicly accessible engagement platform for conservation | Plan created, presented, adopted? | Dave | Leadership Team |  |  | Time: Dave, Engagement Staff Cost: Planning costs (donated?), construction costs (phased, donated?)
|  | Tactic 2A: Convene community stakeholders to understand what the community needs/wants from a conservation engagement platform | Groups engaged | Maria | Planning Professionals |  |  | Time: Dave, LT Cost: Planning costs (donated?)
|  | Tactic 2B: Research similar facilities in similar communities to understand and learn from other orgs' successes/challenges in this space | Research summary created | Maria |  |  |  | Time: Dave, LT Cost: Research costs (donated?)
|  | TACTIC 3: Pending approval of Tactic 2, scope, plan, build capacity for capital campaign to support the project | Board endorsement of campaign | Carol | Dave |  |  | Costs in 2028 could include outsourcing feasibility study to campaign consultant. Volunteer recruitment costs | [18 empty] | Feasibility study | Formation of strategy and volunteer teams
|  | TACTIC 4: Launch campaign | $ raised Volunteers engaged Corporate partnerships established New grant partners established | Carol | Campaign Chair | Dave to Adjust |  | Costs likely in 2029 Campaign coordinator Volunteer squad (size TBD based on scale of campaign) Budget: 10% of campaign goal (TBD based on specifics of Tactic #2)* *Would need more resources for communication/marketing than were allocated for IION | [20 empty] | Launch capaign | Campaign execution
| Strategy #2: Build out capacity to support conservation work in priority areas identified in Idaho by Q4 2027. | Tactic 1: (From Carol--also in Objective 3, Strategy 5) Collaborate with Conservation Director to build portfolio of donors of means who can be tapped for specific conservation projects on an ad hoc basis | 10 projects per conserve staff member in the development folder. | Mike | Carol | $14K (Duplicate from Objective 3) |  | Special Projects Funding Portfolio: Conserve team identifies projects and "stories" Phil/Comm team handles design/production of marketing assets (print and digital) Phil/Comm identifies donor prospects Conservation and Phil/Comm partner for specific project solicitations |  |  |  | Conserve team develops projects to be included |  |  |  | Phil/Comm to develop marketing: Design $1500 Production $5000 Digital integration (website, storymap) $7500 | [5 empty] | Identify and solicit donors: $2500 for donor engagement activities Staff/volunteer TIME
|  | Tactic 2: Develop a robust conservation special projects fund. Fund designed to pay trasaction and/or due dilligence costs for high value projects. Define: "Robust," and "High value" | Special Projects Fund campaign vision, strategy, plan created | Mike | Carol |  |  | See above
| Strategy #2b: Develop one new “Community Conservation” site by Q4 2027. | Tactic 3: Find the ID community conservation project: - Engage the community - Enlist input from public leaders - Assess regional needs and opportunities - Determine feasibility, deepen parks/agency partnerships TAP INTO EXISTING RESOURCES from LTA, other sources. Don't reinvent the wheel |  | Mike | Todd |  | Community engagement/ charrette costs | Kootenai County engagement plan?
| Strategy #3: Strengthen leadership connections and working relationships between Tribal partners and INLC to learn from one another, support Tribal efforts to reconnect to ancestral lands, and advance shared conservation objectives. | Tactic 1: Seek educational opportunites, examples from other land trusts, experts in tribal relations | Shared learning identified and conducted? | Dave | LT/ Board Chair |  |  | Time: staff and board Cost: minor investment, though many free resources | [6 empty] | Dave Out | Dave Out | Dave Out
|  | Tactic 1A: Gather partners (Tribes, Land Trusts, relevant partners) for community building, education, collaboration, and relationship building | Event held? Summary report created? | Dave | LT/ Board Chair | Event costs? | [8 empty] | Dave Out | Dave Out | Dave Out
|  | Tactic 2: Identify key tribal leaders and staff, assign INLC relationship "leads" to cultivate trusting relationships | Relationship matrix created, filled in, used? | Dave | LT/ Board Chair |  |  | Time: Dave and Board Chair | [6 empty] | Dave Out | Dave Out | Dave Out
|  | Tactic 3: Create a plan for inviting tribal representation into INLC board leadership positions, or additional advisory capacity as appropriate | Board: recruitment plan created and implemented? | Board Chair |  |  |  | Time: Board Chair
|  | Tactic 3A: Create opportunities for hiring tribal members into open staff positions | Staff: hiring plan created and implemented? | Dave |  |  |  | Time: Board Chair Cost: Job boards (minimal) | [6 empty] | Dave Out | Dave Out | Dave Out
|  | Tactic 4: Practice patience, forgiveness, understanding, perserverance, and ongoing learning | Regular practice of sharing successes and challenges at board and staff meetings | All |  |  |  | Time: all
| Strategy #4: Launch a “future leaders” internship and/or student outreach program by QX of X year to develop next generation conservation professionals, with emphasis on recruiting Tribal members, women, people of color, and other under-represented groups in conservation. Keep in Touch with these kids - invite them to return, what are they doing? | Tactic 1: Create a program prospectus that is both a survey of what other land trusts (and/or other orgs) are doing and an initial vision of what our program could look like, paired with some preliminary budget numbers | Plan and budget created? | Intern | Dave | Intern Stipend |  | Time: Dave and Intern | [6 empty] | Dave Out | Dave Out | Dave Out
|  | Tactic 1a: Leadership Team decides when to launch the Future Leaders Internship program |  | Leadership Team
|  | Tactic 2: Engagement lead builds this program into their work plan and includes program budget in future Operating Budget | Plan and budget created? | Maria | Maria |  | Costs TBD | Time: Engagement Director
| Strategy #5: Create a new INLC Engagement function and strategy by QX of X year to increase outreach and participation of community members (individuals, families, conservation allies, corporations, etc.) by X% through events, educational opportunities, and volunteer work. | Tactic 1: Create an initial Engagement Program scope and position. Include this in a 2026 Operating Budget as per timing/ roll-out decisions |  | Dave |  |  | Senior FTE | Cost in 2026: Engagement Director salary, support staff, program costs | [6 empty] | Dave Out | Dave Out | Dave Out
| Strategy #6: Launch a brand marketing and visibility effort in 202X to strengthen INLC’s profile and guide strategic outreach and participation in key community initiatives and convenings. | Tactic 1: buildout and budget |  | Maria |  |  |  | Social media management by BigTop to maintain momentum in the interim: $2,200/month (March-December) $22,000
|  | Tactic 2: Assess current brand awareness and applicability (utilizing feasibility studies and strategic plan research) to determine need and scope |  | Maria
| Strategy #7: Identify restoration priorities and expand a coordinated volunteer program by QX of 202X to grow new and existing relationships through hands-on service and restoration work. | TACTIC 1: Develop a model (similar to the Conserve model) that would identify high priority properties for restoration including factors like partner service area or interest, wetland or stream data, wildlife data, adjacency, etc. (Same as Objective 1, Strategy 4, Tactic 2) | Create a set of at least 10 priority restoration properties, and conduct outreach by 2030. | Rose | Mike (?) |  |  | GIS, stewardship staff time. | [6 empty] | R&D OF MODEL |  | USE MODEL
|  | TACTIC 2: Seek out restoration partners, corporate partners, or funding sources that could implement INLC-facilitated restoration projects on private lands or preserve properties identified in the new model. (Same as Objective 1, Strategy 4, Tactic 3) | All "active" restoration projects are supported by conservation partner expertise and fully funded by grants or corporate partners | Rose | Carol or Maria (for corp. partner support) |  |  | Project dependent - determine costs as we go, and plan to get them fully funded by grants or other funders. | [6 empty] | INTERVIEW PARTNERS |  | USE MODEL, RECRUIT SUPPORT/FUNDING
|  | TACTIC 3: Build capacity to host outdoor events by training a portion of the "future leaders" in field study and volunteer engagement basics to expand the capacity of events, and the footprint of the work on the land. | # of intern-led events per quarter # of events hosted per quarter overall | Rose | Steven |  |  | Identify costs in 2025 | PETE RESEARCHING | [11 empty] | TRAIN INTERNS PER TEAM PLAN
|  | TACTIC 4: Build consistency in storytelling about volunteer and land steward work in all formats to promote good stewardship and involvement and bolster INLC's position as a stewardship and volunteer-oriented organization. | # stewardship stories shared about volunteers, landowners, projects, practices, etc. per quarter. | Rose | Maria |  |  | Idenfity costs in 2025 - ideally low or no-cost (volunteer writers, etc.) | PLAN |  |  | IMPLEMENT | [8 empty] | PLAN | IMPLEMENT |  |  | PLAN | IMP | PLAN | IMP | PLAN | IMP
|  | TACTIC 5: Deepen relationships with partners by expanding volunteer programing to partner project areas to expand range of impact, diversify experience for volunteers, and genuinely support our partners. | # of Partnered Events per year Create, maintain, develop "Seat at the Table" with our partners | Rose | _ |  |  | Identify costs in 2025 - event tabling costs, staff time. | PLAN |  |  | IMPLEMENT | [8 empty] | PLAN | IMPLEMENT |  |  | PLAN | IMP | PLAN | IMP | PLAN | IMP
|  | TACTIC 6: Dedicate at least one field work day per month to engaging students on the land, and incorporate relationship building with school programs into workflow for all stewardship staff. | # students engaged per quarter # students incorporated into "future leaders" prog. | Rose | Steven, Engagement Lead | Field Guide Printing costs: $4500 |  | Identify costs in 2025 | PLAN |  |  | IMPLEMENT | [8 empty] | PLAN | IMPLEMENT |  |  | PLAN | IMP | PLAN | IMP | PLAN | IMP
|  | TACTIC 7: Meaningfully engage corporate partners on the land, guided by the identification and recruitment procedures developed as part of Objective 3, Strategy 4, Tactic 2. | # of Corporate Partners $ Raised from Corporate Partners # of Members recruited Amount of shared marketing | Rose | Steven, Maria, Ben | Captured elsewhere |  | Build "ask" to cover costs $1500 to support outreach/engagement with potential corporate partners Develop marketing similar to conservatoin portfolio (expensive--to land in 2026 IF engagement plan/team is in place) | SUPPORT CORPORATE PARTNERSHIP DEVELOPMENT AS NEEDED |  |  |  |  | REVIEW |  |  |  |  | CONTINUE FIELD SUPPORT
(Pending merger with DHC) Strategy: Evaluate, maintain and/or adapt DHC engagement and educational programming to fit within the merged organization and shared goals.
3. Diversify and grow the human and financial resources of our organization to achieve long-term conservation impact. | Strategy #1: Recruit, develop, and retain staff and board talent with the diverse backgrounds, skills, and experiences needed to drive progress on our 2030 goal. | TACTIC 1: Use the Implementation Plan to create a multi-year org chart and hiring plan which will inform multi-year budgeting | Multi-year budget presented to board in November '25 | Dave | Leadership Team |  |  | Time: Dave | [6 empty] | Dave Out | Dave Out | Dave Out
|  | TACTIC 2: Governance Committee to create and implement a multi-year board recruitment plan | Recruitment plan created by July '25 | Governance Chair |  |  |  | Time: Governance Chair and committee members
|  | TACTIC 2A: Governance Committee implements recruitment plan | Board members recruited as per plan? | Governance Chair |  |  |  | Time: Governance Chair and committee members
|  | TACTIC 3: Consider future staff position of Tribal Program Lead | Decision made? | Dave | Leadership Team |  |  | Time: Dave / Leadership Team Cost: Staff salary and program costs | [6 empty] | Dave Out | Dave Out | Dave Out
|  | TACTIC 4: Continue completing annual performance reviews with expectations directly tied to strategic plan. | Performance evals tied to Strat Plan and conducted annually | Dave | Leadership Team |  |  | Time: Dave / Leadership Team | [6 empty] | Dave Out | Dave Out | Dave Out
|  | Tactic 5: Reinforce culture of accountability, celebrate achievements, reward performance. | Salary and bonuses tied to results Poor performance results in change | Dave | Leadership Team | bonuses | salary increases beyond COL | Cost: Staff salaries and bonuses | [6 empty] | Dave Out | Dave Out | Dave Out
|  | Tactic 5A: Evaluate and strive to prevent staff burnout. Use this plan to focus and prioritize work. | "To Stop" work lists created? | Dave | Leadership Team |  |  | Timeline affected if staff resources are insufficient
| Strategy #2: Occupy office space/facilities by 2027 that support the growing staff and demonstrates INLC’s commitment to its full service region in WA and ID. | TACTIC 1: Evaluate needs/opportunities for ID office space. Conduct a quick analysis of properties owned by the Meyers to understand whether asking for donated office space makes any sense. Strategically act on this decision | Action taken? | Dave | Mike |  |  | Time: Dave and Mike, possibly Carol and Sandy pending decisions | [6 empty] | Dave Out | Dave Out | Dave Out | [13 empty] | March 1 ID office lease renewal
|  | TACTIC 2: Assess current and future facilities needs - survey staff for what they want to see. Develop criteria for desired future facilities, including office space, education space, a plant nursery, or other spaces indicated by other parts of the strategic plan. | A "shopping list" for what we want | Ops Director |  |  |  | Time: Ops Director | [22 empty] | start after Dave gets back from sabbatical
|  | TACTIC 3: Create and implement a timeline and funding plan for acquiring new office space(s) or improving existing spaces. | Timeline and funding plan; begin fundraising as needed | Ops Director |  |  |  | Time: Ops Director Cost: Facilities purchase, lease pending decisions
|  | TACTIC 4: Hold an open house(s) to introduce the new space(s) to our constituents and market the new space as a sign of our commitment to the region. | Completed events/member satisfaction | Maria |  |  |  | Event costs, marketing costs | [10 empty] | v | [11 empty] | timing depends on when we acquire a new facility
| Strategy #3: Conduct an org-wide tech systems audit and develop a multi-year plan and budget by 2026 for investments, maintenance, storage, replacement, and troubleshooting. | TACTIC 1: Conduct the systems audit by end of 2025. Develop an implementation plan and budget that prioritizes cyber security. | list of priority projects to implement immediately; cyber security policies and response plan | Ops Director |  | Intellitect $2,000; Tech Soup tech support $56 per issue |  | staff, Intellitect, TechSoup? |  | Intellitect in process | [20 empty] | include in revised budget for board to approve March 2025
|  | TACTIC 2: Hire a consultant to provide full-service managed IT and designate an in-office tech contact to work with the consultant. REACH OUT TO OTHER NONPROFITS, WHAT ARE THEY DOING? | have tech consultant on-board COMMUNITY FOUNDATION? | Ops Director |  | 3000 | 10000 | Tech Impact - budget TBD | [22 empty] | have consultant on board by April
|  | TACTIC 3: With assistance from the consultant, develop a plan and budget for acquiring, maintaining, and/or replacing hardware and software for the next 5 years. | a plan and budget; then implementation of the plan | Ops Director |  |  |  | Tech Impact/staff - budget TBD | [22 empty] | depends on results of assessment, staffing, etc.
| Strategy #4: Grow donor base by X% by 2030 by strengthening acquisition, cultivation, and retention in collaboration with the Engagement Program. Break this into giving level tiers | Tactic 1: Create a plan and budget for a 3-5 year direct-mail campaign to purchased mailing lists | Proposal created? Included in budget? | Carol |  |  |  | Time: Carol |  |  |  | First purchased mailing list: included in IION Budget
|  | TACTIC 1A: Pending approval of plan, implement | Metrics as per plan | Carol |  | $10,000 already included in 2025 budget for IION | Would need to add $10-12,000 for 2026 | Time: Carol, Gillian Cost: Direct mail
|  | Tactic 2: Identify and recruit key corporate partners with shared values to amplify INLC messaging and incentivize Conservancy membership | # of Corporate Partners $ Raised from Corporate Partners # of Members recruited Amount of shared marketing | Carol | Engagement Lead/ Development Committee | $1500 to support outreach/engagement with potential corporate partners Develop marketing similar to conservatoin portfolio (expensive--to land in 2026 IF engagement plan/team is in place)
|  | Tactic 3: Develop marketing/advertising plan (and budget) to communicate message to a wider audience |  | Maria |  | $22K Social Media Support |  | Cost in 2025 (Listed in Objective #2, Strategy 2B, Tactic 3--social media support from contractor)
|  | TACTIC 3A: Communicate the strategic plan |  | Maria
|  | Tactic 4: Develop or maintain high-profile community benefit projects in Kootenai and Spokane Counties Tactic 4A: Develop communication strategy re. these projects |  | Mike |  |  |  | Engagement in CDA; we just have to show up there (Chamber committees, Idaho Community Foundation Innovia, etc.)
|  | FOR ALL EVENTS: TAKE GREAT PICTURES TO CREATE READY-MADE MARKETING CONTENT | SHARED APPROACH BETWEEN DEVELOPMENT AND ENGAGEMENT | Maria |  |  |  | TIME!!!
| Strategy #5: Building on the success of the It’s In Our Nature campaign, sustain momentum of private giving at X%+ of total revenue from annual donations, major gifts/bequests, and grants, while cultivating and expanding the pipeline of future support from new and existing donors. | Tactic 1: Hire additional Philanthropy Team member | $250k in revenue in year 1 $500k in revenue in year 2 $750k in revenue in year 3 $1M/annually by year 4 Planned giving revenue is impossible to predict but the org stands to benefit in the neighborhood of $5M within the next 5-10 years | Carol |  | Manager level FTE |  | One FTE hired in early 2026
|  | Tactic 1a: plan and implement a planned gift cultivation strategy (Wilson, Haman, others?) PART OF MAJOR DONOR STRATEGIES |  | Major Gifts Officer | Carol, Cons. Team |  |  | Time
|  | Tactic 1b: Develop a procedure for integrating large unrestricted gifts WHILE MAINTAINING FLEXIBILITY |  | Carol | Major Gifts |  |  | TIME
|  | Tactic 2: Recruit, educate, engage, and hold accountable a board committed to amplifying the Conservancy's fundraising success |  | Development Committee | Governance Chair |  |  | Time |  |  |  | Contingent on development committee
|  | Tactic 3: Fully develop donor stewardship portfolios for key staff and board members--complete with goals, metrics, and ongoing accountability for engagement |  | Carol | Development Committee | I want to change Gillian to a Specialist and give her a pay bump. |  | Time: Leadership staff and (ideally) board/development committee |  | Beta testing already in progress
|  | Tactic 4: Collaborate with Conservation Director to build portfolio of donors of means who can be tapped for specific conservation projects on an ad hoc basis |  | Carol | Mike |  |  | See info on Objective #2, Tactic 1 & 2
|  | Tactic 5: Implement the grants plan. With and emphasis on moving towards multi-year grants - bring bigger ideas that are fundable over multiple years. |  | Carol | LT |  |  | Time, cost (contractor?) |  | Beta testing already in progress
|  | Tactic 6: (FOR DISCUSSION) Conduct multiple, mini, project campaigns (Special Projects and/or Cons Opp) to complete conservation projects | Beware restricted funds. MAKE ALL OF THIS PART OF A LARGER, GENERAL, UMBRELLA "ASK" AND CAMPAIGN | Carol | Philanthropy Team/ Conserve Team |  |  | See info on Objective #2, Tactic 1 & 2
| Strategy #6: Identify and develop viable earned income and/or other non-philanthropy funding streams to further diversify INLC’s revenue model by 2030. | Tactic 1: Research funding models of other non-profits--land trusts, orgs of similar size, orgs that are the size INLC hopes to be, etc., to identify effective models | LANDSCAPE SURVEY, LOOK TO LTA RESOURCE CENTER | Leadership Team |  |  |  | Consultant?? Scott Schaffer
|  | Tactic 1a: plan and implement learnings from above |  | Leadership Team
|  | Tactic 2: Forecast future potential income streams (Haman) |  | Leadership Team
(Pending merger with DHC) Strategy: Welcome and integrate DHC staff, continuing board members, volunteers, facilities, partners, and donors.
Note on C11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Mike Crabtree Can you please add more detail to this one?
Note on C17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Mike Crabtree Please add more detail to this tactic
Note on C22: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Mike Crabtree A bit more detail here, please. Who and how?
Note on C48: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Mike Crabtree Please break this out in a way that makes sense

## OBJECTIVE 2 (2)
INLAND NORTHWEST LAND CONSERVANCY (INLC) |  | Color Codes:
2030 Plan Implementation |  | Red: Start now
Green: Start later
VISION: People across our region collaborating together to conserve the natural lands, waters, and open spaces that sustain and enrich life, fostering nature's resilience for generations to come |  | Yellow: Start is conditional on something else
MISSION: Protect and care for the lands and waters essential to life and the well-being of communities in the Inland Northwest.
2030 GOAL: Accelerate the permanent protection of 15K acres of priority lands, habitats, and open spaces in the region.
OBJECTIVES | STRATEGIES | TACTICS/PLANS | METRICS |  |  | TEAM LEADS | TEAM SUPPORT | ANTICIPATED CAPACITY AND BUDGET IMPLICATIONS |  |  | SEQUENCE AND SCHEDULE OF WORK | [21 empty] | KEY DATES
[11 empty] | FY25 | [11 empty] | FY26 |  |  |  | FY27 |  | FY28 |  | FY29
[8 empty] | 2025 | 2026 |  | Jan | Feb | Mar | April | May | June | July | Aug | Sept | Oct | Nov | Dec | Q1 | Q2 | Q3 | Q4 | Q1/Q2 | Q3/Q4 | Q1/Q2 | Q3/Q4 | Q1/Q2 | Q3/Q4
1. Develop and execute a robust portfolio of well-resourced conservation projects to achieve key milestones toward our 2030 goal. | Strategy #1: Define INLC’s service area and complete Evaluation and Development of 50+ priority area projects in WA and ID by 2030. | TACTIC 1 - Resource delegation for implementation of the Priority Area plan. Determine goals for outreach and projects with in each Priority area (updated annual work plans.) Delegate staff hours needed to complete annual goals. | Outreach onDevelop and maintain 10 projects per conserve staff member in the development folder. | 1.1.1 | 1.1 | Mike |  |  |  | Currently staffed up. | ONGOING
|  | TACTIC 1A: Public Communication of this plan |  | 1.1.1A | 1.1 | Carol |  | 2500 |  | Staff time Graphics and Printing Costs
|  | TACTIC 2 - Complete annual outreach with 50 landowners and 20 conservation professionals throughout the INLC service area. Document conservation barriers that prevent successful permanent land protection. |  | 1.1.2 | 1.1 | Conserve Team |  |  |  | Currently staffed up.
|  | TACTIC 3: To define INLC's service area, work with Palouse Land Trust to delineate our work areas in Shoshone County. Continue to communicate with Kaniksu Land Trust when projects are located in Bonner County. Work in partnership when it benefits the project. | INLC's Serv ice Area Defined Each staff stewards a list of XX conservation professional and land managers. | 1.1.3 | 1.1 | Mike |  |  |  | Currently staffed up.
|  | Tactic 4: Develop a "stable" of inactive projects that are ready to go and waiting on funding. |  | 1.1.4 | 1.1 | Todd |  |  |  | Currently staffed up.
[6 empty] | Mike |  |  |  | Currently staffed up.
| Strategy #2: Define "Community Conservation" objectives and criteria by Q3 2025 to ensure intentionality, rigor, and structure to land protection projects that serve Objective #2. | Tactic 1 - Define a Community Conservation Project. What is a willing landowner? How does feasibility effect selection? How long should a project take? Bring proposal. Go through LPC. Engage members of community--what level? PLEASE KEEP IN MIND THAT COMMUNITY CONSERVATION PROJECT SELECTION WILL REMAIN A BIT MORE SUBJECTIVE. LET'S NOT TRY TO CREATE A COMPLETELY OBJECTIVE TOOL FOR IDENTIFYING AND SELECTING | Outreach through the RCO Cons Planning process. Engaging community leaders. Working with nonprofits. Tribal input. | 1.2.1 | 1.2 | Todd | Mike |  |  | Currently staffed up.
|  | Tactic 2 - Develop project selection and evaluation tool for Community Conservation Projects. | Outcome will be a evaluation tool that we fill out when evaluating a Community Conservation Project | 1.2.2 | 1.2 | Todd | Mike |  |  | Currently staffed up.
|  | Tactic 3 - Clarify policy and uses for the Conservation Opportunity and Special Projects fund. | Conserve team make proposals for changes to policy. Reveiwed by directors. Approved by board. | 1.2.3 | 1.2 | Conserve Team | Dave |  |  | Currently staffed up. | [6 empty] | Dave Out | Dave Out | Dave Out
| Strategy #3: Deepen collaboration with organizational and agency partners and funders to maximize success in our priority areas and with "community conservation" projects. | Tactic 1: Expand conservation partnerships with organizations that support land protection. Explore more funding through State and Federal sources. | Identify funding gaps for all projects. Funding sources: RCO, RCPP, ALE, Forest Legacy, Restoration Partnership. | 1.3.1 | 1.3 | Mike |  |  |  |  | ONGOING
|  | Tactic 2: Leverage partnerships with higher capacity conservation organizations to get projects done. | Fill project funding gaps with private funding sources. | 1.3.2 | 1.3 | Mike | Dave | [9 empty] | Dave Out | Dave Out | Dave Out
|  | Tactic 3: Remain nimble, adaptive, and resilient WRT shifting conservation funding landscape |  | 1.3.3 | 1.3 | All | [10 empty] | Dave Out | Dave Out | Dave Out
|  | Tactic 4: Anticipate and lean into complex funding strategies | Develop a plan for micro-campaigns for funding. Expand a list of conservation buyer by 3X. Link federal/state funding with private org funding. | 1.3.4 | 1.3 | Mike | All
| Strategy #4: Enhance and restore the conservation values of our properties by maintaining strong landowner relationships, monitoring and ensuring 100% easement compliance, and securing $XK for this work by 2030. | TACTIC 1: Develop or implement more robust monitoring tools including remote programs, aerial monitoring options like LightHawk, and fine-tune Landscape to capture a more thorough annual report for protected properties. | All properties monitored annually using 33% less staff time and resources. | 1.4.1 | 1.4 | Rose | _ |  |  | Identify costs in 2025, and incorporate hire of additional CE steward before 2030. |  |  | RESEARCH |  | USE AND MAINTAIN REMOTE MONITORING SYSTEMS AS NEEDED TO MEET 33% STAFF TIME REDUCTION
|  | TACTIC 2: Develop and implement a model that would identify high priority conserved properties for restoration including factors like partner service area or interest, wetland or stream data, wildlife data, adjacency, etc. | Create a set of at least 10 priority restoration properties, and conduct outreach by 2030. | 1.4.2 | 1.4 | Rose | Mike (?) |  |  | GIS, stewardship staff time. | [6 empty] | R&D OF MODEL |  | USE MODEL
|  | TACTIC 3: Seek out restoration partners, corporate partners, or funding sources that could implement INLC-facilitated restoration projects on private lands or preserve properties identified in the new model. | All "active" restoration projects are supported by conservation partner expertise and fully funded by grants or corporate partners | 1.4.3 | 1.4 | Rose | Carol or Maria(for corp. partner support) |  |  | Project dependent - determine costs as we go, and plan to get them fully funded by grants or other funders. | [6 empty] | INTERVIEW PARTNERS |  | USE MODEL, RECRUIT SUPPORT/FUNDING
|  | TACTIC 4: Host regular (annual or bi-annual) landowner gatherings and communications to build community, enhance trust with the organization, and to introduce landowners to resources that may help them improve habitat value or land use practices on their easement properties. | ___% conversion to members/donors, reduction in potential violations and active communication, more landowner-led habitat enhancement projects conducted. | 1.4.4 | 1.4 | Rose | Maria (communication tools) |  |  | Identify costs in 2025 | PLANNING |  |  | IMPLEMENTATION AND MAINTENANCE | [8 empty] | PLAN | IMPLEMENT |  |  | PLAN | IMP. | PLAN | IMP. | PLAN | IMP.
|  | TACTIC 5: Build capacity to carry out stewardship projects by training a portion of the "future leaders" in field study, monitoring, and best practices to expand the impact of the stewardship team on protected lands, including partner project lands and privately held conservation easement properties. | Supports tactic #1, all properties monitored annually using 33% less paid staff time and resources. | 1.4.5 | 1.4 | Rose | _ |  |  | Identify costs in 2025 | PETE RESEARCHING | [11 empty] | TRAIN INTERNS PER TEAM PLAN
| Strategy #5: Catalyze conservation support and outcomes by informing Spokane and Kootenai County land use decisions and county/state funding, and supporting the advocacy platforms of the Idaho Coalition of Land Trusts (ICOLT) and Washington Association of Land Trusts (WALT). | Tactic 1: Recruit an Advocacy Committee chair | Committee chair picked and committee formed | 1.5.1 | 1.5 | Board Chair
|  | Tactic 1A: Recruit committee members. Adopt Committee Charter. Define staff liaison roles, responsibilities and capacity |  | 1.5.1A | 1.5 | Advocacy Chair
|  | Tactic 2: Become more closely informed of and engaged in WALT, LTA, and ICOLT advocacy positions and process, transferring knowledge back to INLC Advocacy Committee |  | 1.5.2 | 1.5 | Advocacy Committee | Advocacy Committee Staff Liaison
|  | Tactic 3: Create an Advocacy Committee work plan that adequately scans the landscape and anticipates land use planning issues/opportunities, conservation funding issues/opportunities in order to respond and engage in a timely, proactive manner |  | 1.5.3 | 1.5 | Advocacy Chair | Advocacy Committee
|  | TACTIC 3A: Engage the public/our supporters in our advocacy "asks" |  | 1.5.3A | 1.5 | Maria
|  | Tactic 4: Create a tracking and reporting mechanism for documenting successes and setbacks in order to evaluate whether the effort is resulting in more land conserved |  | 1.5.4 | 1.5 | Advocacy Chair
| (Pending merger with DHC) Strategy: Create, integrate, and advance a new Dishman Hills Priority Area and conservation plan. | Begin outreach for adjacent landowners and DHC prioirty properties. |  |  |  | Mike | DHC Committee |  |  | YES
2. Build a broader community of conservation allies and champions by (re)connecting people to the land and expanding partnerships, education, and engagement opportunities. | Strategy #1: Formulate a clear vision and implementation plan by QX of X year for retaining, investing in, and fully leveraging part of the Glen Tana parcel as a large-scale, inclusive, and publicly accessible engagement platform for conservation. | TACTIC 1: Develop and present a short-term ownership vision, budget, and funding plan to the board that addresses the liability of the house while leaning in to the opportunities of the nursery, preserve management, and community engagement (possibly with some "temporary" program improvements like a shelter) | Plan created, presented, adopted? | 2.1.1 | 2.1 | Dave | Rose and Steven |  |  | Time: Steven, Rose, and Dave | [6 empty] | Dave Out | Dave Out | Dave Out
|  | TACTIC 1A: Implement short-term plan | Plan implemented? | 2.1.1A | 2.1 | Rose | Steven | TBD - From Rose and Steven |  | Cost: Demolition and site prep costs (perhaps donated?) |  |  | Fundraise/Friendraise
|  | TACTIC 1B: Plan and implement community engagement programming at GT using the "temporary" site improvements | People engaged Program funding secured | 2.1.1B | 2.1 | Maria | Steven |  |  | Time: Steven, Engagement staff Costs: Program costs
|  | TACTIC 2: Develop and present a long-term ownership vision, budget, and funding plan to the board that fully leverages the property as a large-scale, inclusive, and publicly accessible engagement platform for conservation | Plan created, presented, adopted? | 2.1.2 | 2.1 | Dave | Leadership Team |  |  | Time: Dave, Engagement Staff Cost: Planning costs (donated?), construction costs (phased, donated?)
|  | Tactic 2A: Convene community stakeholders to understand what the community needs/wants from a conservation engagement platform | Groups engaged | 2.1.2A | 2.1 | Maria | Planning Professionals |  |  | Time: Dave, LT Cost: Planning costs (donated?)
|  | Tactic 2B: Research similar facilities in similar communities to understand and learn from other orgs' successes/challenges in this space | Research summary created | 2.1.2B | 2.1 | Maria |  |  |  | Time: Dave, LT Cost: Research costs (donated?)
|  | TACTIC 3: Pending approval of Tactic 2, scope, plan, build capacity for capital campaign to support the project | Board endorsement of campaign | 2.1.3 | 2.1 | Carol | Dave |  |  | Costs in 2028 could include outsourcing feasibility study to campaign consultant. Volunteer recruitment costs | [18 empty] | Feasibility study | Formation of strategy and volunteer teams
|  | TACTIC 4: Launch campaign | $ raised Volunteers engaged Corporate partnerships established New grant partners established | 2.1.4 | 2.1 | Carol | Campaign Chair | Dave to Adjust |  | Costs likely in 2029 Campaign coordinator Volunteer squad (size TBD based on scale of campaign) Budget: 10% of campaign goal (TBD based on specifics of Tactic #2)* *Would need more resources for communication/marketing than were allocated for IION | [20 empty] | Launch capaign | Campaign execution
| Strategy #2: Build out capacity to support conservation work in priority areas identified in Idaho by Q4 2027. | Tactic 1: (From Carol--also in Objective 3, Strategy 5) Collaborate with Conservation Director to build portfolio of donors of means who can be tapped for specific conservation projects on an ad hoc basis | 10 projects per conserve staff member in the development folder. | 2.2.1 | 2.2 | Mike | Carol | $14K (Duplicate from Objective 3) |  | Special Projects Funding Portfolio: Conserve team identifies projects and "stories" Phil/Comm team handles design/production of marketing assets (print and digital) Phil/Comm identifies donor prospects Conservation and Phil/Comm partner for specific project solicitations |  |  |  | Conserve team develops projects to be included |  |  |  | Phil/Comm to develop marketing: Design $1500 Production $5000 Digital integration (website, storymap) $7500 | [5 empty] | Identify and solicit donors: $2500 for donor engagement activities Staff/volunteer TIME
|  | Tactic 2: Develop a robust conservation special projects fund. Fund designed to pay trasaction and/or due dilligence costs for high value projects. Define: "Robust," and "High value" | Special Projects Fund campaign vision, strategy, plan created | 2.2.2 | 2.2 | Mike | Carol |  |  | See above
| Strategy #2b: Develop one new “Community Conservation” site by Q4 2027. | Tactic 3: Find the ID community conservation project: - Engage the community - Enlist input from public leaders - Assess regional needs and opportunities - Determine feasibility, deepen parks/agency partnerships TAP INTO EXISTING RESOURCES from LTA, other sources. Don't reinvent the wheel |  | 2.2B.3 | 2.2B | Mike | Todd |  | Community engagement/ charrette costs | Kootenai County engagement plan?
| Strategy #3: Strengthen leadership connections and working relationships between Tribal partners and INLC to learn from one another, support Tribal efforts to reconnect to ancestral lands, and advance shared conservation objectives. | Tactic 1: Seek educational opportunites, examples from other land trusts, experts in tribal relations | Shared learning identified and conducted? | 2.3.1 | 2.3 | Dave | LT/ Board Chair |  |  | Time: staff and board Cost: minor investment, though many free resources
|  | Tactic 1A: Gather partners (Tribes, Land Trusts, relevant partners) for community building, education, collaboration, and relationship building | Event held? Summary report created? | 2.3.1A | 2.3 | Dave | LT/ Board Chair | Event costs?
|  | Tactic 2: Identify key tribal leaders and staff, assign INLC relationship "leads" to cultivate trusting relationships | Relationship matrix created, filled in, used? | 2.3.2 | 2.3 | Dave | LT/ Board Chair |  |  | Time: Dave and Board Chair
|  | Tactic 3: Create a plan for inviting tribal representation into INLC board leadership positions, or additional advisory capacity as appropriate | Board: recruitment plan created and implemented? | 2.3.3 | 2.3 | Board Chair |  |  |  | Time: Board Chair
|  | Tactic 3A: Create opportunities for hiring tribal members into open staff positions | Staff: hiring plan created and implemented? | 2.3.3A | 2.3 | Dave |  |  |  | Time: Board Chair Cost: Job boards (minimal)
|  | Tactic 4: Practice patience, forgiveness, understanding, perserverance, and ongoing learning | Regular practice of sharing successes and challenges at board and staff meetings | 2.3.4 | 2.3 | All |  |  |  | Time: all
| Strategy #4: Launch a “future leaders” internship and/or student outreach program by QX of X year to develop next generation conservation professionals, with emphasis on recruiting Tribal members, women, people of color, and other under-represented groups in conservation. Keep in Touch with these kids - invite them to return, what are they doing? | Tactic 1: Create a program prospectus that is both a survey of what other land trusts (and/or other orgs) are doing and an initial vision of what our program could look like, paired with some preliminary budget numbers | Plan and budget created? | 2.4.1 | 2.4 | Intern | Dave | Intern Stipend |  | Time: Dave and Intern | [6 empty] | Dave Out | Dave Out | Dave Out
|  | Tactic 1a: Leadership Team decides when to launch the Future Leaders Internship program |  | 2.4.1A | 2.4 | Leadership Team
|  | Tactic 2: Engagement lead builds this program into their work plan and includes program budget in future Operating Budget | Plan and budget created? | 2.4.2 | 2.4 | Maria | Maria |  | Costs TBD | Time: Engagement Director
| Strategy #5: Create a new INLC Engagement function and strategy by QX of X year to increase outreach and participation of community members (individuals, families, conservation allies, corporations, etc.) by X% through events, educational opportunities, and volunteer work. | Tactic 1: Create an initial Engagement Program scope and position. Include this in a 2026 Operating Budget as per timing/ roll-out decisions |  | 2.5.1 | 2.5 | Dave |  |  | Senior FTE | Cost in 2026: Engagement Director salary, support staff, program costs | [6 empty] | Dave Out | Dave Out | Dave Out
| Strategy #6: Launch a brand marketing and visibility effort in 202X to strengthen INLC’s profile and guide strategic outreach and participation in key community initiatives and convenings. | Tactic 1: buildout and budget |  | 2.6.1 | 2.6 | Maria |  |  |  | Social media management by BigTop to maintain momentum in the interim: $2,200/month (March-December) $22,000
|  | Tactic 2: Assess current brand awareness and applicability (utilizing feasibility studies and strategic plan research) to determine need and scope |  | 2.6.2 | 2.6 | Maria
| Strategy #7: Identify restoration priorities and expand a coordinated volunteer program by QX of 202X to grow new and existing relationships through hands-on service and restoration work. | TACTIC 1: Develop a model (similar to the Conserve model) that would identify high priority properties for restoration including factors like partner service area or interest, wetland or stream data, wildlife data, adjacency, etc. (Same as Objective 1, Strategy 4, Tactic 2) | Create a set of at least 10 priority restoration properties, and conduct outreach by 2030. | 2.7.1 | 2.7 | Rose | Mike (?) |  |  | GIS, stewardship staff time. | [6 empty] | R&D OF MODEL |  | USE MODEL
|  | TACTIC 2: Seek out restoration partners, corporate partners, or funding sources that could implement INLC-facilitated restoration projects on private lands or preserve properties identified in the new model. (Same as Objective 1, Strategy 4, Tactic 3) | All "active" restoration projects are supported by conservation partner expertise and fully funded by grants or corporate partners | 2.7.2 | 2.7 | Rose | Carol or Maria (for corp. partner support) |  |  | Project dependent - determine costs as we go, and plan to get them fully funded by grants or other funders. | [6 empty] | INTERVIEW PARTNERS |  | USE MODEL, RECRUIT SUPPORT/FUNDING
|  | TACTIC 3: Build capacity to host outdoor events by training a portion of the "future leaders" in field study and volunteer engagement basics to expand the capacity of events, and the footprint of the work on the land. | # of intern-led events per quarter # of events hosted per quarter overall | 2.7.3 | 2.7 | Rose | Steven |  |  | Identify costs in 2025 | PETE RESEARCHING | [11 empty] | TRAIN INTERNS PER TEAM PLAN
|  | TACTIC 4: Build consistency in storytelling about volunteer and land steward work in all formats to promote good stewardship and involvement and bolster INLC's position as a stewardship and volunteer-oriented organization. | # stewardship stories shared about volunteers, landowners, projects, practices, etc. per quarter. | 2.7.4 | 2.7 | Rose | Maria |  |  | Idenfity costs in 2025 - ideally low or no-cost (volunteer writers, etc.) | PLAN |  |  | IMPLEMENT | [8 empty] | PLAN | IMPLEMENT |  |  | PLAN | IMP | PLAN | IMP | PLAN | IMP
|  | TACTIC 5: Deepen relationships with partners by expanding volunteer programing to partner project areas to expand range of impact, diversify experience for volunteers, and genuinely support our partners. | # of Partnered Events per year Create, maintain, develop "Seat at the Table" with our partners | 2.7.5 | 2.7 | Rose | _ |  |  | Identify costs in 2025 - event tabling costs, staff time. | PLAN |  |  | IMPLEMENT | [8 empty] | PLAN | IMPLEMENT |  |  | PLAN | IMP | PLAN | IMP | PLAN | IMP
|  | TACTIC 6: Dedicate at least one field work day per month to engaging students on the land, and incorporate relationship building with school programs into workflow for all stewardship staff. | # students engaged per quarter # students incorporated into "future leaders" prog. | 2.7.6 | 2.7 | Rose | Steven, Engagement Lead | Field Guide Printing costs: $4500 |  | Identify costs in 2025 | PLAN |  |  | IMPLEMENT | [8 empty] | PLAN | IMPLEMENT |  |  | PLAN | IMP | PLAN | IMP | PLAN | IMP
|  | TACTIC 7: Meaningfully engage corporate partners on the land, guided by the identification and recruitment procedures developed as part of Objective 3, Strategy 4, Tactic 2. | # of Corporate Partners $ Raised from Corporate Partners # of Members recruited Amount of shared marketing | 2.7.7 | 2.7 | Rose | Steven, Maria, Ben | Captured elsewhere |  | Build "ask" to cover costs $1500 to support outreach/engagement with potential corporate partners Develop marketing similar to conservatoin portfolio (expensive--to land in 2026 IF engagement plan/team is in place) | SUPPORT CORPORATE PARTNERSHIP DEVELOPMENT AS NEEDED |  |  |  |  | REVIEW |  |  |  |  | CONTINUE FIELD SUPPORT
(Pending merger with DHC) Strategy: Evaluate, maintain and/or adapt DHC engagement and educational programming to fit within the merged organization and shared goals.
3. Diversify and grow the human and financial resources of our organization to achieve long-term conservation impact. | Strategy #1: Recruit, develop, and retain staff and board talent with the diverse backgrounds, skills, and experiences needed to drive progress on our 2030 goal. | TACTIC 1: Use the Implementation Plan to create a multi-year org chart and hiring plan which will inform multi-year budgeting | Multi-year budget presented to board in November '25 | 3.1.1 | 3.1 | Dave | Leadership Team |  |  | Time: Dave | [6 empty] | Dave Out | Dave Out | Dave Out
|  | TACTIC 2: Governance Committee to create and implement a multi-year board recruitment plan | Recruitment plan created by July '25 | 3.1.2 | 3.1 | Governance Chair |  |  |  | Time: Governance Chair and committee members
|  | TACTIC 2A: Governance Committee implements recruitment plan | Board members recruited as per plan? | 3.1.2A | 3.1 | Governance Chair |  |  |  | Time: Governance Chair and committee members
|  | TACTIC 3: Consider future staff position of Tribal Program Lead | Decision made? | 3.1.3 | 3.1 | Dave | Leadership Team |  |  | Time: Dave / Leadership Team Cost: Staff salary and program costs | [6 empty] | Dave Out | Dave Out | Dave Out
|  | TACTIC 4: Continue completing annual performance reviews with expectations directly tied to strategic plan. | Performance evals tied to Strat Plan and conducted annually | 3.1.4 | 3.1 | Dave | Leadership Team |  |  | Time: Dave / Leadership Team | [6 empty] | Dave Out | Dave Out | Dave Out
|  | Tactic 5: Reinforce culture of accountability, celebrate achievements, reward performance. | Salary and bonuses tied to results Poor performance results in change | 3.1.5 | 3.1 | Dave | Leadership Team | bonuses | salary increases beyond COL | Cost: Staff salaries and bonuses | [6 empty] | Dave Out | Dave Out | Dave Out
|  | Tactic 5A: Evaluate and strive to prevent staff burnout. Use this plan to focus and prioritize work. | "To Stop" work lists created? | 3.1.5A | 3.1 | Dave | Leadership Team |  |  | Timeline affected if staff resources are insufficient
| Strategy #2: Occupy office space/facilities by 2027 that support the growing staff and demonstrates INLC’s commitment to its full service region in WA and ID. | TACTIC 1: Evaluate needs/opportunities for ID office space. Conduct a quick analysis of properties owned by the Meyers to understand whether asking for donated office space makes any sense. Strategically act on this decision | Action taken? | 3.2.1 | 3.2 | Dave | Mike |  |  | Time: Dave and Mike, possibly Carol and Sandy pending decisions | [6 empty] | Dave Out | Dave Out | Dave Out | [13 empty] | March 1 ID office lease renewal
|  | TACTIC 2: Assess current and future facilities needs - survey staff for what they want to see. Develop criteria for desired future facilities, including office space, education space, a plant nursery, or other spaces indicated by other parts of the strategic plan. | A "shopping list" for what we want | 3.2.2 | 3.2 | Ops Director |  |  |  | Time: Ops Director | [22 empty] | start after Dave gets back from sabbatical
|  | TACTIC 3: Create and implement a timeline and funding plan for acquiring new office space(s) or improving existing spaces. | Timeline and funding plan; begin fundraising as needed | 3.2.3 | 3.2 | Ops Director |  |  |  | Time: Ops Director Cost: Facilities purchase, lease pending decisions
|  | TACTIC 4: Hold an open house(s) to introduce the new space(s) to our constituents and market the new space as a sign of our commitment to the region. | Completed events/member satisfaction | 3.2.4 | 3.2 | Maria |  |  |  | Event costs, marketing costs | [10 empty] | v | [11 empty] | timing depends on when we acquire a new facility
| Strategy #3: Conduct an org-wide tech systems audit and develop a multi-year plan and budget by 2026 for investments, maintenance, storage, replacement, and troubleshooting. | TACTIC 1: Conduct the systems audit by end of 2025. Develop an implementation plan and budget that prioritizes cyber security. | list of priority projects to implement immediately; cyber security policies and response plan | 3.3.1 | 3.3 | Ops Director |  | Intellitect $2,000; Tech Soup tech support $56 per issue |  | staff, Intellitect, TechSoup? |  | Intellitect in process | [20 empty] | include in revised budget for board to approve March 2025
|  | TACTIC 2: Hire a consultant to provide full-service managed IT and designate an in-office tech contact to work with the consultant. REACH OUT TO OTHER NONPROFITS, WHAT ARE THEY DOING? | have tech consultant on-board COMMUNITY FOUNDATION? | 3.3.2 | 3.3 | Ops Director |  | 3000 | 10000 | Tech Impact - budget TBD | [22 empty] | have consultant on board by April
|  | TACTIC 3: With assistance from the consultant, develop a plan and budget for acquiring, maintaining, and/or replacing hardware and software for the next 5 years. | a plan and budget; then implementation of the plan | 3.3.3 | 3.3 | Ops Director |  |  |  | Tech Impact/staff - budget TBD | [22 empty] | depends on results of assessment, staffing, etc.
| Strategy #4: Grow donor base by X% by 2030 by strengthening acquisition, cultivation, and retention in collaboration with the Engagement Program. Break this into giving level tiers | Tactic 1: Create a plan and budget for a 3-5 year direct-mail campaign to purchased mailing lists | Proposal created? Included in budget? | 3.4.1 | 3.4 | Carol |  |  |  | Time: Carol |  |  |  | First purchased mailing list: included in IION Budget
|  | TACTIC 1A: Pending approval of plan, implement | Metrics as per plan | 3.4.1A | 3.4 | Carol |  | $10,000 already included in 2025 budget for IION | Would need to add $10-12,000 for 2026 | Time: Carol, Gillian Cost: Direct mail
|  | Tactic 2: Identify and recruit key corporate partners with shared values to amplify INLC messaging and incentivize Conservancy membership | # of Corporate Partners $ Raised from Corporate Partners # of Members recruited Amount of shared marketing | 3.4.2 | 3.4 | Carol | Engagement Lead/ Development Committee | $1500 to support outreach/engagement with potential corporate partners Develop marketing similar to conservatoin portfolio (expensive--to land in 2026 IF engagement plan/team is in place)
|  | Tactic 3: Develop marketing/advertising plan (and budget) to communicate message to a wider audience |  | 3.4.3 | 3.4 | Maria |  | $22K Social Media Support |  | Cost in 2025 (Listed in Objective #2, Strategy 2B, Tactic 3--social media support from contractor)
|  | TACTIC 3A: Communicate the strategic plan |  | 3.4.3A | 3.4 | Maria
|  | Tactic 4: Develop or maintain high-profile community benefit projects in Kootenai and Spokane Counties |  | 3.4.4 | 3.4 | Mike |  |  |  | Engagement in CDA; we just have to show up there (Chamber committees, Idaho Community Foundation Innovia, etc.)
|  | Tactic 4A: Develop communication strategy re. these projects | SHARED APPROACH BETWEEN DEVELOPMENT AND ENGAGEMENT | 3.4.4A | 3.4 | Maria |  |  |  | TIME!!!
| Strategy #5: Building on the success of the It’s In Our Nature campaign, sustain momentum of private giving at X%+ of total revenue from annual donations, major gifts/bequests, and grants, while cultivating and expanding the pipeline of future support from new and existing donors. | Tactic 1: Hire additional Philanthropy Team member | $250k in revenue in year 1 $500k in revenue in year 2 $750k in revenue in year 3 $1M/annually by year 4 Planned giving revenue is impossible to predict but the org stands to benefit in the neighborhood of $5M within the next 5-10 years | 3.5.1 | 3.5 | Carol |  | Manager level FTE |  | One FTE hired in early 2026
|  | Tactic 1a: plan and implement a planned gift cultivation strategy (Wilson, Haman, others?) PART OF MAJOR DONOR STRATEGIES |  | 3.5.1A | 3.5 | Major Gifts Officer | Carol, Cons. Team |  |  | Time
|  | Tactic 1b: Develop a procedure for integrating large unrestricted gifts WHILE MAINTAINING FLEXIBILITY |  | 3.5.1B | 3.5 | Carol | Major Gifts |  |  | TIME
|  | Tactic 2: Recruit, educate, engage, and hold accountable a board committed to amplifying the Conservancy's fundraising success |  | 3.5.2 | 3.5 | Development Committee | Governance Chair |  |  | Time |  |  |  | Contingent on development committee
|  | Tactic 3: Fully develop donor stewardship portfolios for key staff and board members--complete with goals, metrics, and ongoing accountability for engagement |  | 3.5.3 | 3.5 | Carol | Development Committee | I want to change Gillian to a Specialist and give her a pay bump. |  | Time: Leadership staff and (ideally) board/development committee |  | Beta testing already in progress
|  | Tactic 4: Collaborate with Conservation Director to build portfolio of donors of means who can be tapped for specific conservation projects on an ad hoc basis |  | 3.5.4 | 3.5 | Carol | Mike |  |  | See info on Objective #2, Tactic 1 & 2
|  | Tactic 5: Implement the grants plan. With and emphasis on moving towards multi-year grants - bring bigger ideas that are fundable over multiple years. |  | 3.5.5 | 3.5 | Carol | LT |  |  | Time, cost (contractor?) |  | Beta testing already in progress
|  | Tactic 6: (FOR DISCUSSION) Conduct multiple, mini, project campaigns (Special Projects and/or Cons Opp) to complete conservation projects | Beware restricted funds. MAKE ALL OF THIS PART OF A LARGER, GENERAL, UMBRELLA "ASK" AND CAMPAIGN | 3.5.6 | 3.5 | Carol | Philanthropy Team/ Conserve Team |  |  | See info on Objective #2, Tactic 1 & 2
| Strategy #6: Identify and develop viable earned income and/or other non-philanthropy funding streams to further diversify INLC’s revenue model by 2030. | Tactic 1: Research funding models of other non-profits--land trusts, orgs of similar size, orgs that are the size INLC hopes to be, etc., to identify effective models | LANDSCAPE SURVEY, LOOK TO LTA RESOURCE CENTER | 3.6.1 | 3.6 | Leadership Team |  |  |  | Consultant?? Scott Schaffer
|  | Tactic 1a: plan and implement learnings from above |  | 3.6.1A | 3.6 | Leadership Team
|  | Tactic 2: Forecast future potential income streams (Haman) |  | 3.6.2 | 3.6 | Leadership Team
(Pending merger with DHC) Strategy: Welcome and integrate DHC staff, continuing board members, volunteers, facilities, partners, and donors.
Note on C11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Mike Crabtree Can you please add more detail to this one?
Note on C17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Mike Crabtree Please add more detail to this tactic
Note on C22: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Mike Crabtree A bit more detail here, please. Who and how?
Note on C48: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Mike Crabtree Please break this out in a way that makes sense