## Dashboard
INLC 2030 Strategic Plan Dashboard
#VALUE! | [9 empty] | Last Updated: November 12, 2025
| Total Acres Conserved (2025) |  |  |  | Average Priority Projects in Pipeline |  |  | Progress to 15,000 Acre Goal
| 1490 |  |  |  | 30.25 |  |  | 9.933%
| Total Active Donors (2025) |  |  |  | Volunteer Participants (2025) |  |  | Annual Revenue (2025)
| 1120 |  |  |  | 230 |  |  | 2500000
| Year | Acres Goal | Acres Actual | Projects Goal | Projects Actual (avg) | Revenue Goal | Revenue Actual
| 2025 | 1500 | 1490 | 50 | 30.25 | 2600000 | 2500000
| 2026 | 2000 | 0 | 50 | 0 | 2700000 | 2800000
| 2027 | 2500 | 0 | 50 | 0 | 2800000 | 4009000
| 2028 | 3000 | 0 | 50 | 0 | 2900000 | 2000000 | Quarter | Acres | Projects | % Complete
| 2029 | 3000 | 0 | 50 | 0 | 2950000 | 0 | Q1 2025 | 320 | 15 | 85.33%
| 2030 | 3000 | 0 | 50 | 0 | 3000000 | 0 | Q2 2025 | 350 | 36 | 93.33%
[8 empty] | Q3 2025 | 320 | 20 | 85.33% |  |  | Year | Acres Goal | Acres Actual
[8 empty] | Q4 2025 | 500 | 50 | 133.3% |  |  | 2025 Q1 | 375 | 205
[14 empty] | 2025 Q2 | 375 | 375
[12 empty] | Achieved | Remaining | 2025 Q3 | 375 | 500
[12 empty] | 2500000 | 100000 | 2025 Q4 | 375 | 375
| Objective | 2025 Target | 2025 Actual | % Complete | Status
| OBJ-1: Conservation Portfolio | 3,000 acres | 1490 | 49.67% | #VALUE!
| OBJ-2: Community Engagement | 300 volunteers | 230 | 76.67%
| OBJ-3: Organizational Growth | $2.6M revenue | 2500000 | 96.15%

## Overview & Dashboard
INLC 2030 Strategic Plan - Tracking Dashboard
Last Updated: 11/4/2025
PRIMARY 2030 GOAL: CONSERVE 15,000 ACRES
Metric | 2025 Target | 2025 Current | % Complete | By 2030 | Status
Total Acres Conserved | 3000 |  | 0% | 15000
Priority Projects | 50 |  | 0% | 50
Annual Operating Revenue | 2600000 |  |  | 3000000
Total Active Donors | 1250 |  | 0% | 1500
Major Donors Engaged | 39 |  | 0% | 50
Volunteer Participants | 300 |  | 0% | 500
THREE STRATEGIC OBJECTIVES
Objective | Key 2025 Target |  | Current Status | % Complete
OBJ-1: Conservation Portfolio | 3,000 acres & 50 projects
OBJ-2: Community Engagement | 300 volunteers, ID expansion
OBJ-3: Organizational Growth | $2.6M revenue, 1,250 donors

## Acres Conservation Goal
15,000 Acres Conservation Target (2025-2030)
Year | Q1 Target | Q1 Actual | Q2 Target | Q2 Actual | Q3 Target | Q3 Actual | Q4 Target | Q4 Actual | Annual Target | Annual Actual | Cumulative Target | Cumulative Actual | % of 15K Goal
2025 | 375 | 320 | 375 | 350 | 375 | 320 | 375 | 500 | 1500 | 1490 | 1500 | 1490 | 9.933%
2026 | 500 |  | 500 |  | 500 |  | 500 |  | 2000 | 0 | 3500 | 1490 | 9.933%
2027 | 625 |  | 625 |  | 625 |  | 625 |  | 2500 | 0 | 6000 | 1490 | 9.933%
2028 | 750 |  | 750 |  | 750 |  | 750 |  | 3000 | 0 | 9000 | 1490 | 9.933%
2029 | 750 |  | 750 |  | 750 |  | 750 |  | 3000 | 0 | 12000 | 1490 | 9.933%
2030 | 750 |  | 750 |  | 750 |  | 750 |  | 3000 | 0 | 15000 | 1490 | 9.933%

## Priority Projects (50+)
Priority Projects Pipeline (Target: 50+ in pipeline 2030)
Year | Q1 Pipeline Projects | Q1 Actual | Q2 Pipeline Projects | Q2 Actual | Q3 Pipeline Projects | Q3 Actual | Q4 Pipeline Projects | Q4 Actual | Yearly Goal ¦ Average Projects in Pipeline | Annual Average Pipeline Projects | % of 50 Goal
2025 | 50 | 15 | 50 | 36 | 50 | 20 | 50 | 50 | 50 | 30.25 | 60.5%
2026 | 2 |  | 2 |  | 2 |  | 2 |  | 50 | 0 | 0%
2027 | 2 |  | 2 |  | 2 |  | 2 |  | 50 | 0 | 0%
2028 | 2 |  | 2 |  | 2 |  | 1 |  | 50 | 0 | 0%
2029 | 1 |  | 2 |  | 1 |  | 1 |  | 50 | 0 | 0%
2030 | 1 |  | 1 |  | 0 |  | 0 |  | 50 | 0 | 0%

## Financial Goals
Financial Growth Targets (2025-2030)
Year | Q1 Revenue | Q2 Revenue | Q3 Revenue | Q4 Revenue | Annual Revenue Target | Annual Revenue Actual | % Growth | Total Donors Target | Total Donors Actual | Major Donors Target | Major Donors Actual
2025 | 650000 | 650000 | 650000 | 650000 | 2600000 | 2500000 |  | 1250 | 1120 | 39 | 14
2026 | 675000 | 675000 | 675000 | 675000 | 2700000 | 2800000 | 12% | 1300 |  | 43
2027 | 700000 | 700000 | 700000 | 700000 | 2800000 | 4009000 | 43.18% | 1350 |  | 46
2028 | 725000 | 725000 | 725000 | 725000 | 2900000 | 2000000 | -50.11% | 1400 |  | 48
2029 | 737500 | 737500 | 737500 | 737500 | 2950000 |  | -100% | 1450 |  | 49
2030 | 750000 | 750000 | 750000 | 750000 | 3000000 |  | #DIV/0! | 1500 |  | 50

## Community Engagement
Community Engagement & Volunteer Targets
Year | Volunteer Participants Target | Volunteer Participants Actual | % of 500 Goal | Volunteer Events Target | Volunteer Events Actual | Idaho Community Events Target | Idaho Community Events Actual | Idaho Community Members Target | Idaho Community Members Actual
2025 | 300 | 230 | 60% | 12 |  | 2 |  | 0
2026 | 350 |  | 70% | 16 |  | 4 |  | 0
2027 | 400 |  | 80% | 18 |  | 5 |  | 0
2028 | 450 |  | 90% | 19 |  | 6 |  | 150
2029 | 475 |  | 95% | 20 |  | 6 |  | 150
2030 | 500 |  | 100% | 20 |  | 6 |  | 150

## 2025 Quarterly Checklist
2025 Quarterly Milestone Checklist
Quarter | Milestone/KPI | Target | Status | Notes
Q1 2025 | Launch strategic plan implementation |  | FALSE
Q1 2025 | Begin IT systems audit |  | FALSE
Q1 2025 | Acres conserved | 750 | FALSE
Q1 2025 | Priority projects |  | FALSE
Q2 2025 | Complete Tribal engagement plan |  | FALSE
Q2 2025 | Define Conservation Opportunity Fund policy |  | FALSE
Q2 2025 | First corporate partner secured |  | FALSE
Q2 2025 | Acres conserved | 750 | FALSE
Q2 2025 | Priority projects |  | FALSE
Q3 2025 | Complete Community Conservation criteria (CRITICAL) |  | FALSE
Q3 2025 | Complete service area delineation |  | FALSE
Q3 2025 | First Idaho community event |  | FALSE
Q3 2025 | First Tribal consultation meeting |  | FALSE
Q3 2025 | Acres conserved | 750 | FALSE
Q3 2025 | Priority projects |  | FALSE
Q4 2025 | Complete IT systems audit |  | FALSE
Q4 2025 | Complete facilities needs assessment |  | FALSE
Q4 2025 | Complete project evaluation tool |  | FALSE
Q4 2025 | Tribal board recruitment plan complete |  | FALSE
Q4 2025 | Acres conserved | 750 | FALSE
Q4 2025 | Priority projects |  | FALSE

## One-Time Milestones
Critical One-Time Milestones (2025-2030)
Year | Quarter | Milestone | Lead Department | Status | Notes
2025 | Q2 | Define Conservation Opportunity Fund policy | Conservation | FALSE
2025 | Q3 | Complete Community Conservation criteria | Conservation | FALSE | CRITICAL
2025 | Q3 | Complete service area delineation | Conservation | FALSE
2025 | Q4 | Complete IT systems audit | Operations | FALSE
2025 | Q4 | Complete facilities needs assessment | Operations | FALSE
2025 | Q4 | Complete project evaluation tool | Conservation | FALSE
2025 | Q4 | Tribal board recruitment plan complete | Board | FALSE
2026 | Q1 | Hire managed IT service consultant | Operations | FALSE
2026 | Q1 | Launch Future Conservation Leaders internship (5 interns) | Engagement | FALSE
2026 | Q2 | First Tribal/Land Trust regional gathering | Executive | FALSE
2026 | Q2 | Complete multi-year board recruitment plan | Board | FALSE
2026 | Q3 | Tribal representation joins board | Board | FALSE
2026 | Q3 | Launch Advocacy Committee | Conservation | FALSE
2026 | Q4 | Complete multi-year staff recruitment plan | Executive | FALSE
2027 | Q1 | Complete 5-year IT plan | Operations | FALSE
2027 | Q2-Q3 | Secure and begin occupancy of expanded office | Operations | FALSE
2027 | Q4 | New Idaho Community Conservation site established | Conservation | FALSE
2027 | Q4 | Glen Tana Phase 2 design complete | Engagement | FALSE
2028 |  | 100% IT plan milestones achieved | Operations | FALSE
2028 |  | Full office expansion complete | Operations | FALSE
2029 |  | Glen Tana Phase 1 completion | Engagement | FALSE